## Initial Plan
TASK | WEEK 1 | WEEK 2 | WEEK 3 | WEEK4 | WEEK 5 | WEEK 6 | WEEEK 7
Requirements Gathering
Design
Implementation
Data
ITEM DETAILS
LIST OF ITEMS
GUI
DISPLAY
MENU
VIEW
SEARCH
ADD
DELETE
UPDATE
Integration of functionalities
Testing
PHASE2
CREATE DB
CONNECT DB
GUI UPDATE
INSERT UPDATE
DELETE SEARCH
TESTING AND DOCUMENTATION

## Schedule Followed
Dates | Prasana | Sanjana | Shruti | Vindhya
2020-02-09 | Worked on understanding the business requirements
2020-02-10 | Planned the timeline of the project
2020-02-11 | Worked on the design of the system and responsibilities of each member
2020-02-12
2020-02-13 | Researched on Java GUI |  | Planned of using ArrayList for the Inventory Management
2020-02-14
2020-02-15 | Research and self-study
2020-02-16
2020-02-17 | Created GUI file usingJavaFrames | Created ProdDetail | Created ProductDetailsUsingList.java | Created View.java using JavaFrames
2020-02-18 | Created Second.java and Search.java using JavaFrames | Created Add and delete backend code |  | Created Delete.java using JavaFrames
2020-02-19 | Created Search and List for Backend |  | Created Add.java using JavaFrames | Created backend code for update.
2020-02-20 |  | Created Update.java using JavaFrames | Created backend for View and Search.
2020-02-21 | Discussed the issues while implementing the functionalites and started working on Integration
2020-02-22
2020-02-23 | Research and self-study
2020-02-24
2020-02-25 | Integration
2020-02-26 | Unit Testing
2020-02-27
2020-02-28 | Formatting and documentation
2020-02-29 | Research
2020-03-01
2020-03-02 | Create a database
2020-03-03
2020-03-04 | Create connections for the database
2020-03-05
2020-03-06
2020-03-07 | UPDATE GUI
2020-03-08
2020-03-09
10 | CRUD OPERATIONS FUNCTIONALITIES-Updated the INSERT AND UPDATE functionalities |  | CRUD OPERATIONS FUNCTIONALITIES - Updated the DELETE AND SEARCH functionalities
2020-03-03
2020-03-03
2020-03-03
2020-03-15
SPRING BREAK
2020-03-31 | TESTING | TESTING | TESTING | TESTING
2020-04-01
2020-04-02